## Summary Report
Summary Testing Report
Project Name |  | HSD |  |  |  | Current Sprint |  |  | Sprint 1
Created By |  | Joyce - Duong Minh Hieu |  |  |  | Test Period |  |  | 18/09/2023 - 22/09/2023
Buid Version |  | Version:
Project Information |  | 1. Overall Project Progress
|  | Function Name | Sprint No. | Status
|  | Upload File | Sprint 1 | Done
|  | Total | Done | In Progress | Not Started
|  | 1 | 1 | 0 | 0
2. Test case : https://docs.google.com/spreadsheets/d/1yP9TwsAkFgRHe6eE7fnIfJLMHEAOiLkLHFwc0WTdmQ4/edit#gid=1752175820
|  | API |  | Comment
|  | Pass | 1
|  | Fail | 5
|  | Not Started | 0
|  | Total | 6
3. Automation Test
|  | Enviroment execution |  | Assigment enviroment
|  | Time execution |  | 1 minute
|  | Automation Coverage |  | Comment |  |  | Automation Test (High Level) |  | Comment
|  | Manual TCs | 1 |  |  |  | Pass | 1 | When running test scripts - Testing enviroment is not stable
|  | Automation TCs | 5 |  |  |  | Fail | 5
|  | Total | 6 |  |  |  | Block | 0
[7 empty] | Total | 6
Defects List
Bug ID | Title | [5 empty] | Status | Comment
Bug_01 | User can not upload image with .avif format | [5 empty] | To do
Bug_02 | Wrong response code return when user upload invalid image format | [5 empty] | To do
Bug_03 | Wrong response code return when user upload multiple image at the same time | [5 empty] | To do
Bug_04 | Wrong response code return when user upload empty zip file | [5 empty] | To do
Bug_05 | Wrong response code return when user upload invalid zip file | [5 empty] | To do

## Bug Details
Bug ID | Bug Tiltle | Environment | Test Data | Steps | Actual result | Expect result | Screenshot | Severity | Priority | Status | Note
Bug_01 | User can not upload image with .avif format | Assignment Env | curl --location 'https://assessement.onrender.com/api/image' \ --form 'file=@"image.avif"' | 1. Send the POST request to upload .avif file 2. Verify the status code | Status code: 500 | Status code: 200 | https://github.com/HieuVMO246/qa-assignment/blob/master/data/samplereport/Report.pdf | Critical | High | To do
Bug_02 | Wrong response code return when user upload invalid image format | Assignment Env | curl --location 'https://assessement.onrender.com/api/image' \ --form 'file=@"image.docx"' | 1. Send the POST request with any invalid file 2. Verify the status code | Status code: 403 | Status code: 400 | https://github.com/HieuVMO246/qa-assignment/blob/master/data/samplereport/Report.pdf | Medium | Low | To do
Bug_03 | Wrong response code return when user upload multiple image at the same time | Assignment Env | curl --location 'https://assessement.onrender.com/api/image' \ --form 'file=@"image.png"' | 1. Send the POST request with 2 valid files attached at the same time 2. Verify the status code | Status code: 500 | Status code: 400 | https://github.com/HieuVMO246/qa-assignment/blob/master/data/samplereport/Report.pdf | Medium | Low | To do
Bug_04 | Wrong response code return when user upload empty zip file | Assignment Env | curl --location 'https://assessement.onrender.com/api/zip' \ --form 'file=@"image.zip"' | 1. Send the POST request with empty zip file 2. Verify the status code | Status code: 500 | Status code: 400 | https://github.com/HieuVMO246/qa-assignment/blob/master/data/samplereport/Report.pdf | Medium | Low | To do
Bug_05 | Wrong response code return when user upload invalid zip file | Assignment Env | curl --location 'https://assessement.onrender.com/api/zip' \ --form 'file=@"image.zip"' | 1. Send the POST request with invalid zip file 2. Verify the status code | Status code: 403 | Status code: 400 | https://github.com/HieuVMO246/qa-assignment/blob/master/data/samplereport/Report.pdf | Medium | Low | To do

## Copy of Summary Report 1 (hidden)
Summary Report
Project Name |  | HBT Media Owner |  |  |  | Current Sprint |  |  | 2
Project Manager |  | Nguyen Van A |  |  |  | Test Period |  |  | 1/2/2023 - 1/15/2023 Cut off time: 4h30pm
Test Environment (iOS Device) |  | 1. Main Device 1: iPhone X Device Specification: Software Version: 15.5 Capacity: 64G Model Number: MQAX2LL/A |  |  |  | Test Environment (Android Device) |  |  | 1. Main Device: SamsungS10 Device Specification: One UI Version: 4.1 Android Version: 12 Model Number: SM-G973U1
|  | 2. Main Device 2: iPhone 8 Device Specification: Software Version: 15.6 Capacity: 64G Model Number: MQ752LL/A | [6 empty] | 2. Main Device: Samsung A20 Device Specification: One UI Version: 3.1 Android Version: 11 Model Number: SM-A205F/DS
|  | 3. Cross Device 1: iPhone 11 Device Specification: Software Version: 15.6 Capacity: 64G Model Number: MHDG3VN/A | [6 empty] | 3. Cross Device: Samsung A13 Device Specification: One UI Version: 5.1 Android Version: 13 Model Number: SM-A135F/DS
Buid Version (iOS) |  | Version: Build No. 12 |  |  |  | Buid Version (Android) |  |  | Version: 1.0.15 (21)
Project Information |  | 1. Overall Project Progress
|  | Function Name | Sprint No. | Status
|  | Function A1 | Sprint 1 | Done
|  | Function A2 | Sprint 1 | Done
|  | Function A3 | Sprint 2 | In Progress
|  | Function A4 | Sprint 2 | In Progress
|  | Function A5 | Sprint 3 | Not Started
|  | Function A6 | Sprint 3 | Not Started
|  | Function A7 | Sprint 4 | Not Started
|  | Function A8 | Sprint 4 | Not Started
|  | Function A9 | Sprint 5 | Not Started
|  | Function A10 | Sprint 5 | Not Started
|  | Total | Done | In Progress | Not Started
|  | 10 | 2 | 2 | 6
2. Test case (Insert Link to testcase file)
|  | % (Pass/Total) | Total | Pass | Fail | NT | Enviroment | Comment
|  | 99.75% | 814 | 812 | 2 | 0 | iphone X | Pending: Waiting for confirmation N/A: Not available, 1 testcase belongs to verify Keyboard on Android device. This testcase isn't available in iOS device
|  | 99.75% | 814 | 812 | 2 | 0 | iphone 8
|  | 99.75% | 815 | 813 | 2 | 0 | Samsung S10
3. Remaining Bugs
|  | Severity/Status | Open | In Progress | Resolved | Total | Comment
|  | High | 0 | 0 | 0 | 0
|  | Medium | 3 | 1 | 1 | 5
|  | Low | 8 | 1 | 0 | 9
|  | Total | 11 | 2 | 1 | 14
Critical Defects
Jira ID | Title | [5 empty] | Status | Comment
#11 | Failed to login | [5 empty] | Open
#22 | Failed to register new user | [5 empty] | Open
Remark

## Copy of Summary Report (hidden)
Test Report
Project Name |  | HBT Media Owner |  |  |  |  | Sprint |  |  | 2
Project Manager |  | Nguyen Van A |  |  |  |  | Test Period |  |  | 1/2/2023 - 1/15/2023 Cut off time: 4h30pm
Test Result |  | PASS/FAIL
Test Environment (iOS Device) |  | 1. Main Device 1: iPhone X Device Specification: Software Version: 15.5 Capacity: 64G Model Number: MQAX2LL/A |  |  |  |  | Test Environment (Android Device) |  |  | 1. Main Device: SamsungS10 Device Specification: One UI Version: 4.1 Android Version: 12 Model Number: SM-G973U1
|  | 2. Main Device 2: iPhone 8 Device Specification: Software Version: 15.6 Capacity: 64G Model Number: MQ752LL/A | [7 empty] | 2. Main Device: Samsung A20 Device Specification: One UI Version: 3.1 Android Version: 11 Model Number: SM-A205F/DS
|  | 3. Cross Device 1: iPhone 11 Device Specification: Software Version: 15.6 Capacity: 64G Model Number: MHDG3VN/A | [7 empty] | 3. Cross Device: Samsung A13 Device Specification: One UI Version: 5.1 Android Version: 13 Model Number: SM-A135F/DS
Buid Version (iOS) |  | Version | Build No. 12 |  |  |  | Buid Version (Android) |  |  | Version | 1.0.15 (21)
Overall Project |  | 1. Overall Project Progress
|  | Total | % (Pass/Total) | Pass | Pending | N/A | NT | Enviroment | Comment
2. Test case
|  | Total | % (Pass/Total) | Pass | Pending | N/A | NT | Enviroment | Comment
|  | 815 | 99.75% | 812 | 2 | 1 | 0 | iphone X | Pending: Waiting for confirmation N/A: Not available, 1 testcase belongs to verify Keyboard on Android device. This testcase isn't available in iOS device
|  | 815 | 99.75% | 812 | 2 | 1 | 0 | iphone 8
|  | 813 | 100% | 813 | 2 | 0 | 0 | Samsung S10
3. Remaning Bugs
|  | Severity/Status | Open | In Progress | Resloved | Testing | Total |  | Comment
|  | High | 0 | 0 | 0 | 0 | 0
|  | Medium | 3 | 1 | 1 | 1 | 6
|  | Low | 8 | 1 | 0 | 0 | 9
|  | Total | 11 | 2 | 1 | 1 | 15
Critical Defects
Jira ID | Title | [6 empty] | Status | Comment
#11 | Failed to login | [6 empty] | Open
#22 | Failed to register new user | [6 empty] | Open
Comment